## Bug Metric and Mitigation Plan
Iteration | Score | Action Plan
2 | 1 | Planned to solve during buffer time, but ended up fixing during a PP session.
3 | 7 | Planned to solve during debugging time in the next iteration as the bug was discovered late in the iteration and there were other tasks that needed to be prioritised.
4 | 15 | Bugs were handled during iteration. Other features were pushed back to account for bug solving time.
5 | 107 | Features were all completed with our own testing completed. UAT failed and there is a bug infestation. Using planned debugging time in Iter 6 to solve the bugs. Allocated more Debugging hours in Iter 6.
6 | 30 | Major debugging sessions were conducted based on the results from Iter 5. No need to halt development as functions and UI are already completed. Instead, most of the time in this Iter is spent debugging. Some bugs still found during testing sessions. Managed to solve them before Final Presentation deadline
Metric
| Severity | Description
| Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
| High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
| Critical Impact (10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Action Plan
| Score | Action
| Points < 10 | Use the planned debugging time in the iteration.
| Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Iteration 2
Date | Area of testing | Test Case Descrption | Result Description | Error shown (if any) | Importance/Impact | SOLVED? | SOLVED BY
2017-09-26 | Login Function | Testing Login with incomplete Email ID and correct Password Email ID: "aaravamuthan.pillay.201" password: "qwerty322" | FAIL: Expected error message "email/password is wrong", but was instead redicted to home page (succesful login) | - | Low | 2017-09-26 | Gerald and Shen Ying

## Iteration 3
Date | Area of testing | Test Case Descrption | Result Description | Error shown (if any) | Importance/Impact | SOLVED? | SOLVED BY
2017-10-10 | Bootstrap | Testing update function with correct zip file that consists of the 2 required files | Error shown, unable to update the database | HTTP Status 500 - Exception Report (Null Pointer Exception) | Low | 2017-11-18 | Shen Ying and Denise
2017-10-10 | Bootstrap | Testing update with only 1 of the required file | Error shown, unable to update the database | HTTP Status 500 - Exception Report (Null Pointer Exception) | Low | 2017-10-27 | Shen Ying and Denise
2017-10-10 | Bootstrap (Cloud) | Testing bootstrap function with all 3 correct flies (~500,000 lines of data) | Error shown, but database is updated | 500 Internal Server Error | High | 2017-10-18 | Shen Ying and Wei Kiat

## Iteration 4
Date | Area of testing | Test Case Descrption | Result Description | Error shown (if any) | Importance/Impact | SOLVED? | SOLVED BY
2017-10-12 | Top-k Popular Places | Testing timeframe that is less than 15 minutes after the start of the data window (10:12 is the queried time but the data starts at 10:00) | Returns an error message (caused by an empty result) | Error with queried List! | High | 2017-10-15 | Shen Ying and Wei Kiat
2017-10-21 | Top-k Popular Places | Testing timeframe safely within data window (more than 15 minutes after start and before end of data) | Result shows thousands of devices in one location: 1 SMUSISL3SR3.1 8632 2 SMUSISL3SR3.4 6700 3 SMUSISL3SR3.3 5682 | Nil | High | 2017-10-22 | Hidayat and Gerald
2017-10-20 | Top-k Next Places | Testing first semantic place with timeframe safely within data window (more than 15 minutes after start and before end of data) | Returns an error message (caused by an empty result) | Error with queried List! | High | 2017-10-20 | Shen Ying and Wei Kiat

## Iteration 5
Date | Area of testing | Test Case Descrption | Result Description | Error shown (if any) | Importance/Impact | SOLVED? | SOLVED BY
2017-10-26 | Top k Next Places (JSON) | Result set with more than 1 location with the same count | Even though each place has the same count, the ranks of each place is not the same | - | Low | 2017-10-27 | Shenying and Denise
2017-10-26 | Top k Next Places (JSON) | Semantic place with no users in the first queried window | No result, error shown instead | HTTP Status 500 - Exception Report (Null Pointer Exception) | High | 2017-10-27 | Shenying and Denise
2017-10-26 | Top k Next Places (JSON) | Semantic place with users who do not appear in the second queried window | No result, error shown instead | HTTP Status 500 - Exception Report (Null Pointer Exception) | High | 2017-10-27 | Shenying and Denise
2017-10-26 | Top k Next Places (JSON) | Missing, blank, and invalid origin in request | No result, error shown instead | HTTP Status 500 - Exception Report (Null Pointer Exception) | High | 2017-10-27 | Shenying and Denise
2017-10-26 | Top k Next Places (JSON) | Invalid k (non-integer value) in request | No result, error shown instead | HTTP Status 500 - Exception Report (Number Format Exception) | High | 2017-10-27 | Shenying and Denise
2017-10-26 | Top k Next Places (JSON) | Invalid k (non-numeric value) in request | No result, error shown instead | HTTP Status 500 - Exception Report (Number Format Exception) | High | 2017-10-27 | Shenying and Denise
2017-10-26 | Top k Next Places (JSON) | Invalid k (less than 0 and greater than 10) in request | Format of result is wrong: instead of "messages" : [ "invalid k" ] being shown, "error": "invalid k" is shown instead | - | Low | 2017-10-27 | Shenying and Denise
2017-10-26 | Top k Next Places (JSON) | Invalid date in request | Format of result is wrong: instead of "messages" : [ "invalid date" ] being shown, "error": "invalid date" is shown instead | - | Low | 2017-10-27 | Shenying and Denise
2017-10-26 | Top k Next Places (JSON) | Multiple fields missing or blank in request | Only the error message for the first missing/blank parameter is shown | - | Low | 2017-10-27 | Shenying and Denise
2017-10-27 | Bootstrap | Duplicate row testing Duplicate row pairs: 2-3, 6-7, 8-9, 12-13, 15-16 | Duplicate rows should be 2, 6, 8, 12, 15 | Duplicate rows: 1, 5, 7, 11, 14 | High | 2017-10-27 | Shenying and Denise
2017-10-27 | Bootstrap | Testing semantic place validation Line 2 has SMUSISL7ReceptionAndLobby Line 17 has SMUSISL8FilteringArea Line 44 has SMUSISB4NearLiftLobby | Error should be shown for lines 2, 17, 44 | Error shown for lines 2, 17 only | Low | 2017-10-27 | Shenying and Denise
2017-10-27 | Bootstrap | Testing invalid email without .smu.edu.sg after <school> in demographics.csv Line 2 has email: aaravamuthan.pillay.2016@economics | Error should be shown for line 2 | HTTP Status 500 - String index out of range: -1 | High | 2017-10-27 | Shenying and Denise
2017-10-29 | Top k Popular Places (JSON) | Testing output that has 2 places with the same count Date: 6/2/2017 Time: 11:35 Top: 2 | SMUSISB1NearATM and SMUSISL3LiftLobby should be rank 2 | Only SMUSISB1NearATM is rank 2 | Low | 2017-11-04 | Shenying and Denise
2017-11-04 | Breakdown | Entering breakdown-main.jsp | No result, error shown instead | JWTException from token expiry | High | 2017-11-05 | Yat and Wei Kiat
2017-11-08 | Bootstrap | UAT TC 1 | All location lookup entries cannot be locaded into database | Invalid semantic place | High | 14/11/2017 (Official) Fixed during UAT to allow testing of other TC | Gerald and Wei Kiat
2017-11-08 | Heatmap | UAT TC 456 | Not displaying density 0 places | - | Low | 2017-11-14 | Shenying and Denise
2017-11-08 | Breakdown | UAT TC 789 | Percentages are wrong | - | High | 2017-11-14 | Shenying and Denise
2017-11-08 | Popular Places | UAT TC 10 | Not displaying Rank 1 Location (SMUSISL2StudyArea2(New)), instead only showing Rank 2 as Rank 1 | - | High | 2017-11-14 | Shenying and Denise
2017-11-08 | Popular Places | UAT TC 12 | SR2.4 is displayed as having 9 people instead of 8 | - | High | 2017-11-14 | Shenying and Denise
2017-11-08 | Companions | UAT TC 1314 | No companions found | - | Critical | 2017-11-18 | Shenying and Denise
2017-11-08 | Next Places | UAT TC 151617 | No next places found | - | Critical | 2017-11-14 | Shenying and Denise
2017-11-08 | Group Detection | UAT TC 18192021 | No groups detected | - | Critical | 2017-11-18 | Shenying and Denise
2017-11-08 | Bootstrap/Update | UAT TC 2223 | - | HTTP Status 500 (The system cannot find the file specified) | Critical | 2017-11-18 | Shenying and Denise

## Iteration 6
Date | Area of testing | Test Case Descrption | Result Description | Error shown (if any) | Importance/Impact | SOLVED? | SOLVED BY
2017-11-15 | JSON Authenticate | JSON TC 0 | Error message not in JSONArray | - | Low | 2017-11-18 | Shenying and Denise
2017-11-15 | JSON Bootstrap | JSON TC 2 | num-record-loaded array not sorted by file name | - | Low | 2017-11-18 | Shenying and Denise
2017-11-15 | JSON BLR | JSON TC 6,7,8 | "year" field is saved as a string, not an int | - | Low | 2017-11-18 | Shenying and Denise
2017-11-15 | JSON Popular Places | JSON TC 9,10,11 | "count" field is saved as a string, not an int | - | Low | 2017-11-18 | Shenying and Denise
2017-11-15 | JSON Companions | JSON TC 12,13 | Companions are wrong | - | Critical | 2017-11-18 | Shenying and Denise
2017-11-15 | JSON Group Detect | JSON TC 17,18,19,20 | No groups detected | - | Critical | 2017-11-18 | Shenying and Denise
2017-11-15 | JSON Update | JSON TC 21 | False duplicates in update file | - | High | 2017-11-18 | Shenying and Denise
2017-11-19 | JSON Popular Places | JSON output is not ordered by ascending rank for the following input Date: 2017-02-06T10:30:00 k: 10 | Rank 10 places comes after Rank 1 | - | Low | 2017-11-19 | Hidayatullah and Shenying