## Task Metric
Iteration | Score | Action Plan
1 | 1 | Our estimates are fairly accurate, and we are roughly on track.
2 | 0.88235 | > Re-estimate the tasks for the future iterations. > We decided to integrate MVC and the ConnectionManager class as soon as we could manage it, so that programming for further features is easier. > Moved UI design and JSON integration earlier to also speed up progress down the line.
3 | 0.88235 | > Re-estimate the tasks for the future iterations. > We decided to focus on completing the Breakdown and Next Places functions and JSON integration for completed functions (Bootstrap and Popular Places). > Companions was pushed to the end of Iteration 4’s plan, to allow us to focus on having a suitable demo.
4 | 1 | Our estimates are fairly accurate, and we are roughly on track.

## Mitigation Plan
Score (%) | Action
TM < 50 | Gross under-estimation of the effort required. 1.Immediately inform supervisor about the slip within 24 hours. 2.Then use the same mitigation as the category 50 < TM < 90 and seriously consider dropping tasks.
50 < TM <= 90 | 1. Re-estimate the tasks for the future iterations. 2. Decide on critical functionality to focus on in following iteration.
90 < TM <= 110 | Our estimates are fairly accurate, and we are roughly on track.
110 < TM <= 150 | 1.Re-estimate the tasks for the future iterations.
150 < TM | Gross over-estimation of the effort required. 1. Immediately, inform supervisor about the slip within 24 hours. 2. Then use the same mitigation as the category 110 < SM < 150